## Deliverables Matrix
Category | Specification Section | Deliverable ID | Deliverable Title / Description | Responsible Party (Owner) | Submitting Party | Reviewer / Approving Authority | Supporting Parties | Due Trigger | Required Date | Submission Date | Approval Date | Status | Days Aging | Priority | Schedule Impact | Inspection Impact | Compliance Impact | Related Activity / Phase | Location / Area | Related RFC / Submittal / IR | Closeout Required (Yes/No) | Closeout Date | Document File Location | Comments / Escalation Notes
Submittal | 09 96 23 | SUB-014 | Anti-Graffiti Coating Product Data, VOC, Warranty | General Contractor | Vendor | Architect / Owner | TaskFlow Dynamics | Prior to installation | 2026-01-20 | 2026-01-16 |  | In Review | 9 | High | Blocks installation | Inspection readiness | Compliance requirement | Field installation phase | Exterior walls |  | No |  | /Submittals/SUB-014 | Escalate if review exceeds 14 days
RFC |  | RFC-006 | Scoreboard embed anchor layout clarification | General Contractor | General Contractor | Structural Engineer | TaskFlow Dynamics | Field conflict identified | 2026-02-03 | 2026-01-24 |  | Pending | 6 | High | Blocks concrete placement | Inspection readiness | Structural compliance | Foundation phase | Scoreboard foundation | SUB-014 | No |  | /RFC/RFC-006 | Escalate to engineer and owner
Inspection Request |  | IR-033 | Structural steel weld inspection | General Contractor | General Contractor | DSA Inspector | TaskFlow Dynamics | Pre-weld requirement | 2026-02-03 | 2026-01-30 |  | Requested | 3 | High | Blocks steel erection | Inspection requirement | DSA compliance | Steel erection phase | Scoreboard structure |  | No |  | /Inspections/IR-033 | Confirm inspector availability
Closeout |  | CO-011 | O&M Manuals and Warranty Documentation | Vendor | Vendor | Owner | TaskFlow Dynamics | System startup |  |  |  | Not Started |  | Medium | Blocks turnover | Closeout readiness | Contract compliance | Closeout phase | Entire project |  | Yes |  | /Closeout/CO-011 | Begin collection during installation